**GRAD Update September 2016**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Trust** | **No. of patients screened** | **No. of patients ineligible due to death** | **No. of patients ineligible due to surgery** | **No. of patients ineligible due to other reason eg palliation** | **No. of patients ineligible unknown reason** | **No. of invitations sent to eligible patients** | **First invitations sent** | **Second invitations sent** | **No. consented** | **No. refused** | **Other comments** |
| Barts Health NHS Trust | 774 | 218 | 353 | 57 | 36 | 110 | August 2015 | October 2015 | 38 | 7 | Clinical data still needs to be entered |
| Guy’s and St Thomas NHS Foundation Trust (PIC) | 465 | 194 | 55 | 21 | 37 | 158 | August 2015 | October 2015 | 63 | 11 | Clinical data still needs to be entered  (DOB for 6 required) |
| East & North Hertfordshire NHS Trust (Mount Vernon) |  |  |  |  |  | 276 | November 2015 | They cannot send out second invitations for the initial batch of 191 patients as they had mismatched trial numbers. They will be sending out second invitations to non-responders for the batch of 85 | 41 | 8 |  |
| The Pennine Acute Hospitals NHS Trust |  |  |  |  |  | Still sending out invitations | November 2015 |  | 116 | 25 | Still entering data |
| **Trust** | **No. of patients screened** | **No. of patients ineligible due to death** | **No. of patients ineligible due to surgery** | **No. of patients ineligible due to other reason eg palliation** | **No. of patients ineligible unknown reason** | **No. of invitations sent to eligible patients** | **First invitations sent** | **Second invitations sent** | **No. consented** | **No. refused** | **Other comments** |
| Portsmouth Hospitals NHS Trust |  |  |  |  |  | 110 | December 2015 | August 2016 | 54 | 8 | Problems with database resolved 26/07/2016 – still entering data |
| Royal Surrey County Hospital NHS Foundation Trust |  |  |  |  |  | Still sending out invitations | January 2016 |  | 29 |  | Still entering data |
| Walsall Healthcare NHS Trust |  |  |  |  |  | Still sending out invitations | July 2016 |  | 18 |  | Unable to enter data due to problems with database – unresolved 30/09/2016 |
| The Shrewsbury and Telford Hospital NHS Trust |  |  |  |  |  | Still sending out invitations | August 2016 |  |  |  | Unable to enter data due to problems with database – unresolved 30/09/2016 |
| UCLH (PIC) |  |  |  |  |  |  |  |  |  |  | Still waiting for list of screened patients from Kylie Gyertson |
| **Trust** | **No. of patients screened** | **No. of patients ineligible due to death** | **No. of patients ineligible due to surgery** | **No. of patients ineligible due to other reason eg palliation** | **No. of patients ineligible unknown reason** | **No. of invitations sent to eligible patients** | **First invitations sent** | **Second invitations sent** | **No. consented** | **No. refused** | **Other comments** |
| North Middlesex University Hospitals NHS Trust (PIC) |  |  |  |  |  |  |  |  |  |  | NHS Permissions granted August 2015 but PI retired in June 2015. New PI Anna Thompson – awaiting for minor amendment to be approved |
| **TOTAL:** |  |  |  |  |  | **654** |  |  | **359** | **59** |  |

Other sites:

These sites are awaiting approval under the new HRA Approvals process

1. East Kent Hospitals University NHS Foundation Trust
2. Leeds Teaching Hospitals NHS Trust
3. Barking, Havering and Redbridge University Hospitals NHS Trust
4. University Hospitals Birmingham NHS Foundation Trust
5. Nottingham University Hospitals NHS Trust
6. Norfolk & Norwich University Hospitals NHS Foundation Trust
7. Sheffield Teaching Hospitals NHS Foundation Trust

In addition to collecting and entering more patients, we are now analysing the data for the 359 consented patients to see who can be considered to have severe radiation reactions and which patients can be matched to act as controls with no severe radiation reactions but correspond in terms of tumour site, T & N stages, age, sex, and smoking. These patients will be invited to take part in the second phase of this study to attend a research clinic where we will take their blood and saliva samples.